## Gantt Chart
# | Task Name | Phase | Days | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
1 | Requirements Analysis | Planning | 2 | ✔ DONE
2 | System Architecture Design | Planning | 2 | ✔ DONE
3 | Functional Decomposition – Level 0 | Planning | 1 | ✔ DONE
4 | Functional Decomposition – Level 1 | Planning | 2 | ✔ DONE
5 | Project Setup & Directory Structure | Setup | 1 | ✔ DONE
6 | Config Files (weights, series) | Setup | 2 | ✔ DONE
7 | Disk Cache (Parquet + TTL) | Data Acq. | 2 | ✔ DONE
8 | FRED Fetcher (10 macro series) | Data Acq. | 3 | ✔ DONE
9 | WRDS Fetcher (7 Compustat metrics) | Data Acq. | 3 | ✔ DONE
10 | Technical Fetcher (yfinance, 8 indicators) | Data Acq. | 3 | ✔ DONE
11 | Ticker Resolver (yfinance Search) | Data Acq. | 1 | ✔ DONE
12 | BaseNormalizer & Look-ahead Bias Guard | Normalization | 2 | ✔ DONE
13 | MinMax Normalizer | Normalization | 1 | ✔ DONE
14 | Z-Score Normalizer | Normalization | 1 | ✔ DONE
15 | Percentile Rank Normalizer | Normalization | 1 | ✔ DONE
16 | Normalization Integration Tests | Normalization | 1 | ✔ DONE
17 | MacroScorer | Scoring | 2 | ✔ DONE
18 | FundamentalScorer (GICS sectors) | Scoring | 3 | ✔ DONE
19 | TechnicalScorer (V-shape RSI) | Scoring | 2 | ✔ DONE
20 | Scorer Integration Tests | Scoring | 1 | ✔ DONE
21 | HorizonResult Dataclass | Aggregation | 1 | ✔ DONE
22 | ShortTermHorizon Aggregator | Aggregation | 1 | ✔ DONE
23 | MidTermHorizon Aggregator | Aggregation | 1 | ✔ DONE
24 | LongTermHorizon Aggregator | Aggregation | 1 | ✔ DONE
25 | HTML Dashboard Formatter | Output | 3 | ✔ DONE
26 | JSON / CSV Formatter | Output | 1 | ✔ DONE
27 | Terminal Table (rich library) | Output | 1 | ✔ DONE
28 | CLI Entry Point (main.py) | Output | 2 | ✔ DONE
29 | End-to-End Testing | Testing | 2 | ✔ DONE
30 | Web Application (Flask UI) | Web | 3 | ✔ DONE
31 | Final Review & Documentation | Testing | 2 | ⏳ IN PROGRESS
Progress: 30/31 tasks complete ¦ ✔ Done: 30 · ⏳ In Progress: 1 · ○ Pending: 0
Legend: | ✔ Completed Task | ✔ Completed (Critical) | Critical Path | Normal Task